Livelihood security for Katkari community in Raigad and Thane District

Report For

Onaway Trust, UK

Rainforest Information Centre, Australia

Reporting Period

1 April 2004 to 30 September 2004

Academy of Development Science

Kashele Post, Karjat Taluka, Raigad District

Maharashtra 410 201

Contents

1.	Background	3

2.	Land	4

3.	The ADS team	4-5

4.	Capacity building of ADS team	5

5.	Meetings in villages	6

6.	Survey in Katkari villages	6-7

7.	Identification of problems/ issues	7

8.	Strategy/ action programme	8

9.	Activities implemented	9-

i.	Land rights and land issues	9

a.	Manual on land literacy	10

b.	Legal land deed – 7/12 extract	11

c.	Gaothan/ Gharthan	12-13

d.	Ceiling land	14-16

e.	Registration of legal heir	17-18

f.	Land to the tiller/ unregistered tenants / 32 G	19-20

g.	Dalli/ Eksali Lands	20-21

h.	Forest encroachments	22

i.	Survey of land issues	23-24

- Panchayati Raj	25

- Promoting bio-diverse agriculture in Katkari villages	26

- Collective farming by landless Katkari people	27

- Government food security programme	27-29

- Antyodaya Yojana	30

- Caste certificate	31

- Legal documents and the Katkari community	32

- Legal advice and assistance	33-34

- Education for Katkari children	35

- Media exposure	35

10.	Conclusion	35

11.	Annexures	36-39

a.	Annexure I: Note on Dalli/ Eksali lands	36-39

1.	Background

Much is being discussed about development efforts for the Katkari by Non-Government as well as Government agencies. The Katkari are realising the hard way that just being described as a ‘Primitive Tribal Group’ by the Government does not necessarily mean that they would be given an equal opportunity. On the contrary, the Katkari now have to live with the stigma of a ‘Primitive Tribal Group’ on top of the ‘Criminal Tribe’ tag already secured to their psyche.

Officials of the Tribal Affairs Ministry and the Integrated Tribal Development Project (ITDP) keep talking of resources that have been allocated for the Katkari but whether there is a clear strategy for the development of Katkari is not at all clear. In cases where some initiative is undertaken by the Government, the effort is either short sighted or lopsided. Consequently, a lot of money goes down the drain without any concrete benefits to the community. Thus, many five year plans and sub-plans down the line, the condition of the Katkari continues to stagnate and even deteriorate.

ADS and its partner NGOs have initiated long-term measures to address issues facing the Katkari community in Raigad and Thane Districts of Maharashtra. Efforts have been made to gain a better understanding of the issues and problems and to use this to devise a long-term strategy for the development of the Katkari community.

The Rainforest Information Centre, Australia; Onaway Trust, UK and Grassroots, Germany have provided generous support to the ADS initiative. ADS has approached ITDP with request for specific projects but the bureaucracy has paid nothing but lip service.

Given below are details of the activities implemented during 1 April 2004 to 30 September 2004.

2.	General

ADS has initiated work with the Katkari community in collaboration with other NGOs in Raigad and Thane Districts. Van Niketan (Murbad); Shramik Mukti Sanghatna (Shahpur); SOBTI (Sudhagad-Pali) and Academy of Development Science (Raigad) are the NGO partners engaged in this project. The division of Talukas amongst NGO partners is as follows:

| Taluka | NGO partners |
| --- | --- |
| Shahpur | Van Niketan, Shramik Mukti Sanghatna |
| Murbad | ADS |
| Karjat | ADS |
| Khalapur | ADS |
| Sudhagad-Pali | Sobti |

The report gives details of activities implemented by all the project partners in the five Talukas. Each NGO has its own team to implement the project. ADS itself has put together a team of eight team members for the Katkari project in its working area of Karjat, Khalapur and Murbad Taluka.

The ADS approach has been to first establish a rapport with the Katkari community through informal meetings, discussions and cultural activities. This is followed by efforts to bring about improvements in the livelihoods of Katkari people. A similar approach is followed by other NGO partners.

3.	The ADS team

The word ‘ADS team’ actually refers to ADS and its partner NGOs. Each organisation has put in place its own team of field staff. ADS and partner NGOs are in regular contact through phone and exchange visits to co-ordinate project activities and to monitor progress.

ADS has a team of seven field staff participating in work with the Katkari community under the guidance of Bansi Ghevde, the Project Co-ordinator. From amongst the field staff, two are Katkari, three are Adivasi, two are women and four are non-Adivasi.

Bhagwan Mate (Marathi), Santosh Dangre (Agri), Kaluram Bhagat (Thakur Adivasi), Bhau Pawar (Katkari Male), Ms. Meena Pawar (Katkari Female), Bhagwan Dongre (Agri) and Ms. Kalpana Tamhane (Marathi Female).

While selecting the team, preference was given to Katkari people. However, it was, and is, difficult to get Katkari people who are willing to work consistently on the project over a period of 2-3 years. Most of the Katkari youth are uneducated. The ones who are educated prefer Government jobs. Another important factor is the tendency of Katkari staff to keep changing jobs. Even as the report is being written, one of the Katkari staff, Bhau Pawar, has already left the project while Meena Pawar, the second Katkari member, has given indications that she would be leaving soon. Ideally, it would be wonderful to build a team of Katkari members but it is not possible in reality.

4.	Capacity building of ADS staff

To begin with, ADS has taken up work on capacity building of its team. The methodology adopted is as follows:

Each staff member is allotted five Katkari hamlets for field work. One-day training sessions are organised on different issues for the field staff every Saturday followed by field work in the allotted villages the following week. There is a sharing of experiences of field staff the following Saturday to understand achievements, problems, learnings, etc.

Weekly training/ education camps are organised for the staff on issues like:

Working in Adivasi villages; Katkari community; Katkari culture and traditions; Present status of Katkari community; Government Rules/ Regulations concerning land issues; Government Schemes & Programmes; Functioning of Government Departments; Government Documents; Introduction to basic land documents like 7/12 extract, 8A, changes in land ownership (Form No. 6), etc; Land measurement; Gaothan/ Gharthan; 32 G; Registration of legal heir; Ceiling lands; Land division; Dalli lands; Eksali lands, Caste certificates; Ration Card; Legal issues; etc. The objective is to bring about following improvements in the ADS staff:

Improve their understanding about the Katkari community in terms of livelihoods, culture, traditions, etc; develop a better understanding of Government rules/ regulations; enable them to understand basic land documents; identify problems, if any; plan corrective action; be informed about existing Government schemes/ programmes for the development of Katkari community; conduct surveys; organise meetings in villages; undertake measurement of land; write applications to Government officials; etc.

This process is helping in enhancing capacities of the ADS team in working with the Katkari community in general and in addressing land/ legal issues in particular.

5.	Meetings in villages

Informal visits, discussions, meetings, cultural events, etc. are being organised by NGO partners in Katkari hamlets. In Sudhagad-Pali, the series of meetings gradually led to a big meeting of Katkari people from 50 hamlets. The Katkari people felt that they could use the occasion to revive their traditional “Nyaya Nivada Manch” (dispute redressal forum) which had stopped functioning since the past 10-15 years. As a result, even minor disputes amongst Katkaris were being referred to the Police, who were using the opportunity to exploit both the parties. Moreover, it was leading to increased harassment of Katkaris by the Police. It was decided to organise a meeting of all the 80-85 Katkari hamlets in Sudhagad-Pali Taluka to finalise the Nyaya Nivada Manch. The Katkari elders requested the NGO partner (SOBTI) to suggest a structure and mechanism for the forum to operate in a just and equitable manner. The modalities for the forum are being worked out.

Meetings in villages are taking place regularly since the Katkari families are at home during the monsoon. There will be a break in the meetings once the Katkari families migrate to brick kilns during November-December. Dance, music and other cultural programmes were organised in some of the villages to motivate and mobilise people.

There is a gradual but certain support being offered to the entire process by the Katkari community. The active participation of Katkari people will crystallise in days to come.

6.	Survey in Katkari villages

Survey was conducted in 250 Katkari hamlets (100 in Karjat Taluka, 50 in Khalapur Taluka, 50 in Shahpur Taluka and 50 in Sudhagad-Pali Taluka). The number of villages is much more than the number indicated in the proposal. A need was felt to generate detailed information on individual Katkari hamlets and hence all the hamlets were included in the survey. Survey will be done in many more villages during the next six months. The objective of the survey is to properly understand socio-economic condition; land issues; forest issues; village land ownership; basic amenities; education; health & nutrition; etc. for individual Katkari families and hamlets. A survey format was developed in consultation with Katkari elders, ADS staff, NGO partners and development experts. The survey methodology followed by the ADS team was meetings in villages; informal discussion with Katkari families; house-to-house surveys; discussion with researchers, Government officials; etc.

The survey data is being compiled. Preliminary findings of the survey from all the Talukas indicate that over 70% hamlets do not have a legal Gaothan, 90% families are below the poverty line; 80% families are landless; 70% families are bonded labour; less than 5% families are dependent on agriculture for their livelihoods; 90% families live in temporary huts; etc. The survey hence confirms the general impression that the Katkari community lives in abject poverty – subject to intense exploitation by outsiders.

ADS will analyse the data and prepare a detailed report in Marathi over the next six months. Detailed findings of the survey will be given in the annual report.

The survey findings will be used to identify problems of the Katkari community and to develop long-term action programmes to address their problems. The Survey Report will be submitted to the State Government in efforts to influence state policies on Katkari and other Primitive Tribal Groups.

7.	Identification of problems/ issues

Based on the survey and meetings in Katkari villages, the following problems were identified:

- Total lack of organisation at the village or community level amongst the Katkari.

- Landlessness.

- Indebtedness.

- Bonded labour.

- Lack of education/ literacy.

- Total lack of basic amenities in Katkari hamlets.

- Poor housing conditions.

- Lack of food and nutritional security.

- Lack of access to proper health care facilities.

- Lack of access to legal documents like Caste Certificates, Ration Card, BPL Certificate, etc.

- Absolute exploitation by outsiders.

Identification of problems helped in preparing a comprehensive strategy for development work with the Katkari community.

8.	Strategy/ action programme

An action programme for addressing issues/ problems of the Katkari community has to consider short-term, medium-term and long-term goals.

It was felt that a major factor contributing to persistent poverty amongst Katkari community was the insecure livelihoods based on bonded labour. It was hence decided to focus on addressing the land issues of Katkari people, assist them to access government programmes and enable them to turn to agriculture for their livelihoods.

Work on other issues like housing, basic amenities, education, drinking water, health care, etc. would follow in due course of time. A need to revive Katkari culture and traditions is also seen as an important factor in mobilising and organising the community so that they regain confidence and are proud of their ethnic identity and culture.

9.	Activities implemented

i.	Land Rights and Land Issues

The issue of land ownership assumes critical importance today given the widespread land alienation in Adivasi regions by ever-expanding cities like Mumbai, Pune, Nashik, etc. and the increasing reliance of poor tribal farmers on land for their livelihoods. This is particularly true in the case of Katkari people who are confronted with insecurity of tenures and livelihoods.

The sources of livelihood for the poor in Adivasi regions are undergoing a radical shift from forests-agriculture-wage labour to wage labour-agriculture-forests. Land ownership and gainful livelihoods through land are thus important issues in the fight against poverty in Adivasi regions. As forests dwindle and the poor are forced to part with their land, the only option they have to survive in this unequal world is to end up in the slums of Mumbai. Over the past 15 years the landscape in Karjat Tribal Block has changed considerably from semi-forested and primarily agricultural to one where lavish farm houses and health resorts dominate with barbed wire fences across vast tracts of land. Hordes of city people are seen pouring into the region on weekends in fancy cars to ‘unwind’ and to rejoice. In the process, local Adivasi people and their cattle are losing their traditional footpaths, grazing grounds, lands and livelihoods.

There is a need to immediately put an end to the illegal and forced land alienation taking place in Adivasi regions. This can be done by persistently and forcefully following up with government agencies for the implementation of pro-poor land reforms legislation put in place by the central and state government.

Given the fact that over 80% Katkari families are landless and even those who own land face various problems related to land ownership, it was decided to focus on the land issues of Katkari people.

To begin with, ADS listed land issues prevalent in the Raigad-Thane region. Efforts were then made to compile detailed information about the land issues in individual Talukas through a survey. Information collected during the survey will be compiled and analysed over the next six months. Given below are individual land issues along with the action taken by the ADS team and NGO partners.

a.	Manual on land literacy

Given the lack of literacy about land issues amongst people and also NGOs and activists, the ADS team decided to prepare a Manual to present the seemingly complex information about land issues in a simple language for the lay person. A draft Manual has been prepared in Marathi and has been sent to experts for review and corrections. It will be published during November-December 2004. The Manual deals with the following issues:

- Types of land.

- 7/12 Extract

- Pher Phar (record of change in land ownership).

- Land measurement (how to measure land?).

- Registration of legal heir.

- Land division/ partition.

- Legal ownership of land under cultivation.

- Unregistered tenants, 32 G.

- Dalli Lands.

- Eksali Land.

- Encroachment on Adivasi lands.

- Gharthan/ Gaothan.

- Private Forest Acquisition Act.

- Structure and functions of Government Revenue Department and Tribal Welfare Department.

- Forms for submission of applications pertaining to various land issues.

The Manual will be distributed to Gram Panchayats, NGOs and activists in the work area of ADS.

b.	Legal land deed - 7 / 12  Extract:

The 7/12 Extract is the legal land deed. It is perhaps the most important document pertaining not only to land ownership but also for obtaining legal documents like Caste Certificate, Ration Card, etc; accessing land-based Government Schemes and so on. It also serves to secure bail for the owner in criminal cases filed by the Police.

However, it is extremely difficult for the Katkari community to get the 7/12 Extract for their small pieces of land from the Revenue Officials. ADS organised a campaign to assist Katkari families obtain 7/12 Extracts for their land. A total of 175 Katkari families from 17 villages were assisted to obtain 7/12 Extracts. These documents were then taken to ADS for safe keeping to ensure that they were not lost or taken away by outsiders from the Katkari families. The concept of a “Document Bank” to ensure safety of basic legal documents belonging to poor families of Katkari and other Adivasi groups is discussed later in the report.

During this process it was found that the Katkari community does not know anything about the 7/12 Extract. Outsiders as well as Government officials exploit the ignorance of Katkari people to deprive them of their rights. ADS has hence started to organise education programmes on basic land literacy for Katkari families. Camps have so far been organised in 40 villages.

c.	Gaothan / Gharthan

The land on which a village is located is called Gaothan and the land on which a house is based is called a Gharthan. The Government of Maharashtra has notified in 1961 that any village with 20 or more houses should be given the status of a legal Gaothan irrespective of whether the villages is located on forest land, revenue land or private land. The village should be located on that place for over 12 years. The Government has issued a GR on 20 May 2002 stating that where the number of houses is less than 20, such houses should get a legal Gharthan status even if they are based on private or government land.

Sale of Kotwalwadi village

Kotwalwadi is a sleepy hamlet of 60 families located close to the forest. The village has been in place for as long as the people remember. Things were going on well until one day a non-tribal person who owns land next to the village decided to sell off the land on which more than half the village is located. The person claims that he is the owner of the village land.

The villagers of Kotwalwadi were shocked when they heard about the sale of a part of their village land. For all of them, it meant a loss of their homes in more ways than one. It was a distressing situation and they did not know what to do. They approached the Revenue Official (Talathi) who promised to look into the matter if he was paid a sum of Rs. 1,200 by the five families who were directly affected. He was given an amount of Rs.1,200 but nothing happened for a long time. On the contrary the five families were threatened by the land owner’s goons and asked to pay a sum of Rs.5,000 per family if they wanted to continue staying on their lands. One woman from the five families refused to either give the money or to move their house. She was badly beaten up by the land owner’s thugs!

Villagers sought advice from ADS when they realised that the Revenue Officials were not doing anything, and on the contrary, were hand in glove with the land owner. The ADS team immediately organised a meeting in the village to discuss the situation. All the families were present for the meeting. The atmosphere was volatile since the villagers were demonstrating tendencies of taking up arms against the land owner. The ADS team asked them to cool down and to pursue a legal course of action. Villagers were told about legal provisions pertaining to Gaothan and Gharthan. Villagers realised that they would be able to prevent sale of the land if they remained united and submitted applications for legal Gharthan and Gaothan to the Government. ADS assisted the villagers to prepare and submit applications to the Tehsildar. ADS also assisted them to register a complaint with the Tehsildar against the Revenue Official who had taken Rs.1,200 from them and a police complaint against the three persons who had beaten up the woman.

Seeing that things were going out of control, the Government official came running to the village and gave back the money, claiming he was going to sort out the problem. Acting on the formal complaint, the Police arrested the three thugs and put them in prison. The land owner is now on the defensive and he has stopped talking about selling off the land. ADS will assist the villagers to pursue the case with the Government.

However, in the case of many Katkari and Thakur villages, the ownership of Gaothan is either with the Forest Department, Revenue Department or non-tribal individuals (generally moneylenders). Hence Adivasi families living in such villages always live under the yoke of the landowner. They can neither build better houses nor avail any Government programmes for basic amenities like drinking water, approach roads, etc. in villages. This is particularly true in the case of Katkari people who are often forced and harassed by the landowner to shift their houses from the village. Katkari families without a legal Gaothan and Gharthan thus face permanent insecurity of tenure and a sense of rootlessness.

It was seen through the survey and visits to Katkari villages that between 60-80% Katkari hamlets are without a legal Gaothan. The ownership of Gaothan land is different in different Talukas. For instance, in Khalapur Taluka, most of the Katkari Gaothans are owned by the Forest Department whereas in Karjat and Sudhagad-Pali Talukas, a majority of Katkari Gaothans are claimed by individuals (mainly contractors and moneylenders).

Taking a cue from the Kotwalwadi incidence (see Box above), ADS organised meetings in 100 villages to create awareness about the existing Government rules regarding Gaothan/ Gharthan. This led to the identification of thirteen hamlets which were under intense and immediate pressure from land owners to shift from the land. Out of these, eleven hamlets are located on private land while two are on Forest Land. One of the private owners is a famous producer from the Hindi Film Industry (Bollywood). The ADS team immediately prepared detailed applications for sanction of legal Gaothan for the thirteen hamlets and submitted applications to the District Collector in the last week of September 2004. Details are given below. The process of preparing and submitting formal applications to the Government itself has put some pressure on the land owners and they have stopped harassing the Adivasi families to shift their houses. Further follow up is now in progress. ADS will pursue the matter in the “Lokshahi Din”.

| No. | Name of Katkari village | Houses | Population | Ownership |
| --- | --- | --- | --- | --- |
| 1 | Nadode | 45 | 165 | Private |
| 2 | Hatanolpada | 6 | 35 | Private |
| 3 | Poiwadi 1 | 17 | 64 | Private |
| 4 | Poiwadi 2 | 19 | 112 | Private |
| 5 | Sindhiwadi | 43 | 167 | Forest Department |
| 6 | Nadhal Dandwadi | 8 | 39 | Forest Department |
| 7 | Gohe | 32 | 174 | Private |
| 8 | Murmatwadi | 28 | 134 | Private |
| 9 | Vehaloli | 25 | 115 | Private |
| 10 | Vaitagwadi | 23 | 91 | Private |
| 11 | Kharade | 24 | 101 | Private |
| 12 | Manekhind | 16 | 71 | Private |
| 13 | Savarpada | 25 | 147 | Private |
|  | Total | 311 | 1,415 |  |

ADS will also assist other Adivasi hamlets which do not have a legal Gaothan to submit applications to the Government. As a matter of fact, ADS is co-ordinating with the network of NGOs in Thane and Raigad to compile cases of all villages which do not have legal Gaothan/ Gharthan and make a joint submission to the Government. This will take more time since a lot of work needs to be done by partner NGOs in their own Talukas.

There should not be a sword hanging on the heads of Adivasi families for their homes and villages. ADS is confident that it will be able to assist Adivasi hamlets to retain possession of their household and village lands.

d.	Ceiling Lands

Government has allotted surplus land to some landless families under The Maharashtra Agricultural Land (Ceiling on Holdings Act 1961). However, in many cases, the allotment of Ceiling Land to landless families has taken place only on paper. The concerned families have either not been shown the land or a large plot of land has been allotted to a group of families without subdivision into plots for individual families. Surveys of Ceiling Land have not been done and concerned families have not been given legal possession of the land. In some cases, the original land owner, from whom the land was taken away under the ceiling legislation, continues to cultivate the land. There are also many instances of encroachment by outsiders on ceiling lands allotted to Katkari families. Hence, in reality most Adivasi families who have been allotted Ceiling Lands do not actually have legal possession of the land.

ADS prepared details of the Ceiling Land cases and submitted applications to government officials at various levels. ADS and partner NGOs then posed questions regarding encroachment on ceiling lands of Katkari families in Karjat Taluka in the Legislative Assembly. An application was also submitted to the Deputy Chief Minister, Revenue Minister and Tribal Development Minister. There was pressure on the government to immediately act on the issue given the involvement of a Primitive Tribal Group.

The Government issued orders to the concerned Tehsildar for sorting out the matter on a priority basis. ADS then began following up with the Tehsildar for implementation of the order. The Revenue Department requested the ADS team to be a part of the mission. ADS took up responsibility for collecting legal documents from individual families, motivating people to participate in the surveys, removing grass from the land and acting as a link between Government and people. The Revenue Department was asked to do survey work in 9 Katkari villages of Karjat Taluka. The details of Ceiling Land are as follows:

| No. | Name of Adivasi village | Ceiling Land (in acres) | No. of families | Population |
| --- | --- | --- | --- | --- |
| 1 | Varne Katkariwadi | 32 | 9 | 55 |
| 2 | Mandavne | 45 | 12 | 71 |
| 3 | Male Katkarwadi | 65 | 36 | 212 |
| 4 | Pashane Katkarwadi | 45 | 25 | 154 |
| 5 | Ardhe | 16 | 3 | 20 |
| 6 | Kurkulwadi | 12 | 4 | 22 |
| 7 | Tivre | 9 | 3 | 19 |
| 8 | Vengaon Katkarwadi | 16 | 4 | 28 |
| 9 | Khushivali | 7 | 2 | 11 |
|  | Total | 247 | 98 | 592 |

The Land Survey Department began work but came up with a number of excuses to delay and postpone the surveys. One of the main reasons was a shortage of manpower. The ADS team stepped in and volunteered to assist the Survey team in putting things together at all the sites. The concerned Katkari families were traced to various brick units and asked to return to their villages immediately. Meetings were organised in the villages. The survey work began in the first village (Varne Katkarwadi). It took nearly one month. The second survey was initiated and but could not be completed due to the onset of monsoon. These two are relatively easier plots of land in terms of lack of vegetation. So the survey work was much simpler. A preliminary assessment was done on one of the large plots. There were a number of difficulties. The monsoon began and it was hence decided to postpone the survey work in the remaining eight villages till November.

Katkari families in Varne Katkarwadi were thus able to get legal ownership of their land after a period of over 30 years. Some of them have already started cultivation on the land with the onset of monsoon in June 2004. A major outcome of this success is the optimism amongst Katkari in the entire region. They now feel that some solution can be found for their problems and their sufferings.

In Khalapur, ADS has generated a list of 218 Katkari families in 12 villages who have been given Ceiling Land by the Government. Similarly, there are 245 families from 19 villages in Shahpur Taluka and another 147 families from 20 villages in Sudhagad-Pali Taluka. The ADS team will begin probing the status of Ceiling Lands in Khalapur, Shahpur and Sudhagad-Pali  Talukas over the next six months.

The sequence of events leading to Government action on handing over legal possession of Ceiling Lands to the Adivasi families in Karjat Taluka is as follows:

| No. | Steps of the Campaign | Results/ Outcomes |
| --- | --- | --- |
| 1. | Meetings in villages to discuss Ceiling Land issue | Increased awareness about legal ownership of Ceiling Lands. Systematic documentation of Ceiling Land cases in Karjat Taluka. |
| 2 | Application to the Tehsildar with details of Ceiling Land cases | Tehsildar was sympathetic but did not take any action |
| 3 | Application to the District Collector in the Lokshahi Din | Tehsildar was asked to investigate. Lack of concrete action. |
| 4 | Meetings with Land Survey Department and submission of formal applications for survey of Ceiling Lands in Karjat Taluka | The Land Survey Department declined to do surveys of concerned lands without payment of fees. They also expressed unavailability of time for the surveys. |
| 5 | Question regarding encroachment on Ceiling Lands of Katkari families in Karjat Taluka posed in the Legislative Assembly | The issue was discussed in the Maharashtra Legislative Assembly. The Government was pressurised to act on the matter. The Revenue Minister issued an order to the Deputy Collector for immediate action. A special Revenue Official was appointed to address the problem. |
| 6 | Visits by the Deputy Collector, Tehsildar and other Revenue Officials to verify claims regarding encroachment on Ceiling Lands. | On the spot inspection; discussion with affected Katkari people and discussion with the Land Survey Department. |
| 7 | Joint meeting of Revenue Department officials, Land Survey Department and ADS staff. | Decision to do free surveys, sharing of responsibilities and finalising the survey time table. |
| 8 | Adivasi Land Survey Week | Survey of Ceiling Lands initiated in 9 Katkari villages of Karjat Taluka. Survey completed in Varne Katkarwadi. Survey work discontinued in the other 8 villages till Nov 2004 due to the monsoon. |

e.	Registration of legal heir

Names of many Adivasi persons have not been registered as legal heir on land deeds for over two generations despite the fact that the original owners have passed away a long time back. There are no records pertaining to the death of original owners. The claims of legal heirs have not been registered in legal deeds since land ownership is still in the name/s of individuals who have passed away. The legal heirs are being denied their right to land and on the other hand, the confusion in land ownership is leading to misappropriation of such lands by outsiders who find it easy take away these lands.

Parshuram Navsha Waghmare is a Katkari farmer from Mandavne village in Karjat Taluka. Parshuram is lucky since he owns 3.5 acres of irrigated land which can be used to grow two crops of paddy. Parshuram’s father passed away three years ago and his name was not registered in the land deed. This is what the story is all about.

Following his father’s demise, Parshuram submitted an application to the Talathi to register his name as a legal heir in the land deed. There was no action for over a year despite reminders. The Talathi asked for Rs.1,000 as an unofficial ‘processing fee’. Left with no option, Parshuram gave Rs. 1,000 to the Talathi, feeling that atleast his work would be done. Nine months went by and his name was still not registered. Reminders did not yield any results. Parshuram was now afraid that his land might be misappropriated, like that of so many of his brothers. He happened to meet ADS staff.

ADS submitted an application to the Tehsildar and the Deputy Collector requesting action in Parshuram’s case. The money given to the Talathi was also mentioned. The Tehsildar directed the Talathi to immediately sort out the matter. The Talathi came to Mandavne and registered Parshuram’s name in the land deed. He returned the money. Going beyond, the Talathi also assisted another seven Katkari families in the surrounding villages to register as legal heir.

There is a need to immediately list all the legal heirs and register their names in the land deeds. A major obstacle in this process is getting the death certificates of individuals who are listed as land owners and others who have died without legally inheriting the land. A large number of poor families stand to benefit from the process to register legal heirs.

ADS compiled details of all land cases where the names of legal heirs have not been registered for a long time. An application was submitted to the Tehsildar. The Tehsildar then directed Revenue Officials to organise joint camps with ADS for registering legal heir in different villages. The team consisted of Revenue officials, Sarpanch, Police Patil, Village Panch and ADS staff. ADS mobilised people and encouraged them to come forward to register their names. ADS also did the home work of collecting all legal documents. Details of the camps for registration of legal heir for Ceiling Lands are given below:

| No. | Camp site | Number of legal heirs | Participating villages |
| --- | --- | --- | --- |
| 1 | Mandavne | 15 | Ambewadi, Phanaswadi, Mandavne |
| 2 | Bhaliwadi | 12 | Jambhulwadi, Wadachiwadi, Lakhachiwadi, Pulachiwadi |
| 3 | Varne Katkarwadi | 13 | Varne Katkarwadi, Palasdari Katkarwadi |
| 4 | Neral | 20 | Male, Pashane, Ordhe |
| 5 | Tivre | 6 | Tivre, Posari |
|  | Total | 66 | 15 |

66 persons from 15 villages were thus assisted to register their names as legal heir.

In the case of Dalli Lands, it was found that a large number of people were not registered as legal heir. ADS hence organised Awareness camps in villages with Dalli Lands. The Dalli Plot holders were advised to obtain death certificate of persons whose names are registered in the land deeds or to generate evidence about the death of the land owner through means like: a) passing resolution in the Gram Sabha; b) Verification/ Panchnama by village elders; c) Preparing an Affidavit in the Tehsildar’s office, etc. Details of the awareness camps for the unregistered Dalli Plot holders are given below:

| No. | Name of village | Number of unregistered heir | No. | Name of village | Number of unregistered heir |
| --- | --- | --- | --- | --- | --- |
| 1 | Avlas | 6 | 2 | Mugpe | 8 |
| 3 | Mohili | 7 | 4 | Shirse | 4 |
| 5 | Tamnath | 5 | 6 | Sangvi | 8 |
| 7 | Khandpe | 7 | 8 | Mangaon | 6 |
| 9 | Salpe | 12 | 10 | Kharvandi | 3 |
| 11 | Kondana | 2 | 12 | Chochi | 3 |
| 13 | Vengaon | 12 | 14 | Vadap | 22 |
| 15 | Gourkamat | 17 | 16 | Kushivali | 8 |
| 17 | Koshane | 12 | 18 | Neral | 4 |
| 19 | Damat | 14 | 20 | Borgaon | 8 |
| 21 | Salokh | 9 | 22 | Potalpali | 14 |
| 23 | Asal | 4 | 24 | Palasdari | 12 |
| 25 | Koravli | 6 | 26 | Bhaliwadi | 15 |

Separate camps will be organised for the Dalli Plot holders to register their names once the basic documents are ready.

Efforts are thus being made to identify unregistered legal heir and to assist them register their names on land deeds so that they have a security of tenure and the chances of land alienation or misappropriation are nullified.

f.	Land to the tiller/ Unregistered tenants/ 32 G:

The State has made a provision to give legal ownership of land to persons who have been tilling a particular plot of land for a certain number of years under the “Bombay Tenancy and Agricultural Lands Act 1948”.  The claims of the tenant are registered in the land deed and subsequently a certain amount is fixed as the price of the land which the tenant is directed to pay to the original land owner. The tiller then becomes owner of the land.

Unregistered tenants are farmers who have been tilling Sahukari land for a number of years but do not have their names registered in the land deed. In many cases, these tenants are the original owners of the land they are tilling. The Sahukars or moneylenders have misappropriated the lands from tribals often through fraudulent means. It is possible to register the names of such tenants in the land deed. The legal procedure is as follows:

Form 7B: Proof that the tenant is cultivating crops on the land. This is called Pik Pahani in the official parlance. It literally means a crop survey. These surveys have to be recorded on the land by revenue officials for three consecutive years.

Form 70B: Prove tenancy rights. This can be done by a) producing form 7B (Pik Pahani); b) passing a resolution in the Gram Sabha stating that the tenant has been cultivating the plot of land for so many years; c) affidavits by Police Patil, Sarpanch or a senior citizen of the village confirming the tenancy; d) written proof by neighbours that the tenant has been cultivating the land; etc. If the proof is accepted, the applicant is registered as a tenant on the land deed. The tenant then has to purchase the land from the Sahukar by paying a specific amount as land price (provision in form 32 G).

Sale of land to the tenant (32 G): Tenants who have been able to register their names in the land deed need to purchase the land from the Sahukar. The tenants have to buy the land at 80 to 200 times the amount of tax they pay on the land. For instance, if the tax paid is Rs.5, the tenant has to pay a price of Rs.400 to Rs.1,000 to the Tehsildar. The Tehsildar, in turn, pays the amount to the Sahukar. If the tenant does not have the money, there is a provision for him/her to pay the money in instalments.

Tehsildars have recently issued a notice to all tenants who have been registered for the past 10-15 years to immediately pay the land price and get the lands legally transferred in their names. Failing this, the government would take back these lands from the tenants and give them to other farmers. However, most tenants are either unaware of the legal provisions or do not have the money to pay the land price. There is a real danger that a large number of tenants may lose their claim to lands they have been tilling for a long time if they fail to pay the land price to the government. This provision can be used to take away lands cultivated by poor farmers who are registered tenants.

There is also a provision for the Project Officers, ITDP, to pay the land price to Sahukars on behalf of Adivasi farmers who are below the poverty line (BPL), realising that these farmers may not have the means to pay the land price. Once again, Adivasi farmers find it difficult to avail of this concession.

A number of issues come up in this. For instance, unregistered tenants, 32 G, fixing a price for the land, non-payment of land price, etc. ADS team is creating awareness, identifying farmers affected by some or all of these issues and informing and assisting farmers. For instance, a survey in 20 villages brought out 120 tenants who have not been given a price for their land while another 98 farmers who are unable to pay the land price for one reason or another. ADS is submitting applications to the Tehsildar to fix the land price and also to the Project Officer, ITDP to help pay the land price for tribal farmers who are below the poverty line.

g.	Dalli/ Eksali lands:

Dalli and Eksali lands are plots of land legally given to landless people by the forest department for cultivation of crops. The ownership of Dalli and Eksali plots is with the forest department, although tribals have been cultivating these plots for over 100 years. There is a distinction between Dalli and Eksali systems. The ownership of land in the Dalli system is ‘collective’ while Eksali plots have individual ownership. Dalli is found mainly in Raigad while Eksali is common in Thane and some other Districts of Maharashtra. More than 30,000 Adivasi farmers are cultivating about 60,000 acres of Dalli and Eksali lands in Raigad and Thane Districts alone. Most of these Adivasi families are otherwise landless and many are Katkari. The State Government has issued GRs in 1969, 1970 and 1971 stating that the ownership of Eksali/ Dalli plots cultivated by Adivasi people should be legally handed over to them. However, Adivasi people have not become owners of Dalli / Eksali lands due to the indifferent attitude of state and central government agencies. Civil Society Groups in Raigad and Thane have been campaigning for the implementation of the 1971 order under the banner of Shoshit Jan Andolan for many years but a final decision on the fate of Dalli / Eksali plot holders seems elusive even 30 years after the State Government order to hand over legal possession of the land to the Dalli/ Eksali holders. Thousands of Dalli and Eksali plot owners might lose ownership of the lands they have been cultivating for decades if the State and Central Governments now decide to evict the Adivasi families, citing reservations given in the Forest Conservation Act of 1980. A detailed note on Dalli/ Eksali lands is given in Annexure I.

ADS is documenting the status of Dalli/ Eksali lands in Karjat, Khalapur and Murbad Taluka. It is assisting many unregistered Dalli Plot holders to register their names in the land deeds (details given above). ADS is also assisting and mobilising Dalli Plot holders to utilise the lands productively for growing crops instead of leaving them fallow. The Government could argue that the Dalli/ Eksali holders are no longer cultivating these lands and so there is no need to give the lands to them. Hence it is important that the lands be under cultivation. ADS is assisting poor Katkari families to grow different food crops on Dalli lands by providing seeds, manure, etc.

Writ petitions in High Court

Concerned with the lack of action by the Government and the loss of zeal and co-ordination on part of the Civil Society Campaign, ADS and some partner NGOs decided to resort to legal means to seek redressal for the land issue. ADS has hence filed a Writ Petition for Dalli Lands in the High Court on behalf of a Katkari person, Ram Pandu Mukne, from Bhaliwadi village in Karjat Taluka. Similarly, a second Writ Petition has been filed against the Government for an Eksali Plot in the High Court on behalf of another Katkari person, Maruti Sakhya Waghre, from Talavli village in Khalapur Taluka. There have already been some arguments in the court and the preliminary debate seems favourable to the ADS camp. However, the matter can be indefinitely postponed or even hijacked by the government since the entire machinery is on their sides while ADS seems to be fighting a lonely battle with meagre resources. There are financial constraints in hiring good lawyers and in seeking support from experts. Similarly, the constituents of the campaign on Dalli/ Eksali lands are opposed to the path of Judicial Activism espoused by ADS.  Some other NGOs, though, support the stand taken by ADS.

Nadhal Katkarwadi is a small Katkari hamlet right next to the Mumbai-Pune Highway in Khalapur Taluka. There is a 21-acre Dalli Plot in the name of five families from the village (Dalli Plot No. 52 B, Survey No. 85). The Forest Department had disforested and transferred this plot to the Revenue Department way back in 1974 for handing over possession to the five families. However, the Revenue Department did not take any action and the plot was lying uncultivated. Over a period of years, most of the land surrounding the village was purchased by city people for building farm houses, given the proximity of the village to the Highway and the abundant water from a dam next to the village.

Slowly the farm houses started encroaching on the Dalli Plot since it was prime property. The Katkari families were restless, realising that their land would be eventually taken away by city people. The ADS team reached the village and assisted the five families to file an application for the legal possession of the Dalli Plot. ADS pursued the matter with the Tehsildar, the Deputy Collector, Collector and the Divisional Forest Officer. Finally, the five families were given legal ownership of the Dalli Plot. They have started growing crops on the land. The Katkari families are now secure and have absolutely no fear of anyone taking away their land.

To sum up, the issue of Dalli/ Eksali lands can benefit a large number of poor Adivasi families, particularly the Katkari community. However, the government is deliberately keeping the issue wrapped up and does not have any interest in giving the land to Adivasi people. The civil society groups have more or less lost steam after a prolonged campaign and are divided on what stand is to be taken and who should lead. ADS has now filed Writ Petitions in the High Court and is prepared to go to the Supreme Court if there is favourable support. Given the complexities, the issue may take a long time to resolve.

h.	Forest encroachment

Many Adivasi families have been cultivating crops on lands owned by the forest department since a long time. In some cases, the Forest Department itself had given plots of land to landless families for growing crops in order to reduce pressure on forests. The Government has subsequently decided that all such encroachments should be legalised and concerned Adivasi farmers should be given legal ownership of the plots they have been cultivating over a long period of time (orders of 1978 and 10 October 2002). District administrations have been asked to set up Gao Samitis (village committees) to verify claims of Adivasi farmers regarding forest encroachment and to generate proof of their tenancy rights. However, the Government GR ordering regularisation of encroachments is not being implemented properly. On the contrary, efforts are being made by the Forest Department to evict the tenants.

Application has been submitted to the Tehsildar on behalf of 165 Katkari families from 15 villages in Shahpur Taluka for regularisation of encroachments. Follow up is in progress.

i.	A preliminary survey of land issues

As part of the on-going work, ADS has attempted to document the status of various land issues affecting Adivasi families. It is important to note that this is an absolutely preliminary attempt, a work in progress. ADS does not claim that it is accurate. At this stage, it may only be considered a broad framework. It could also be the tip of an ice berg. The status of land issues may be much worse than what is given here. Unfortunately, neither the Government Revenue Department nor the Tribal Development Department have such consolidated information about the land status of Adivasi families. The results of the survey are given on the following pages. It can be clearly seen that a large number of Adivasi families need assistance in sorting out their land issues.

Land Issues - Statistics from Karjat, Khalapur and Murbad Taluka

| No. | Land Issues | Karjat Taluka |  | Khalapur Taluka |  | Murbad Taluka |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Land in acres | No. of families | Land in acres | No. of families | Land in acres | No. of families | Total land in acres | Total families |
| ### I | ### Dalli / Eksali lands |  |  |  |  |  |  |  |  |
| a | Revenue Dept. (Disforested) | 830 | 87 | 465 | 92 | 0 | 0 | 1,295 | 179 |
| b | Forest Department | 2,485 | 1,375 | 3,022 | 1,353 | 3,062 | 1,250 | 8,569 | 3,978 |
|  | Total Dalli/ Eksali Land | 3,315 | 1,462 | 3,487 | 1,445 | 3,062 | 1,250 | 9,864 | 4,157 |
| II | Other land issues |  |  |  |  |  |  |  |  |
| 1 | Ceiling land | 338 | 146 | 360 | 175 | 450 | 154 | 1,148 | 475 |
| 2 | Unregistered tenants | 2,750 | 815 | 325 | 87 | 1,200 | 250 | 4,275 | 1,152 |
| 3 | 32 G | 800 | 265 | 330 | 120 | 250 | 70 | 1,380 | 455 |
| 4 | Forest encroachments | 315 | 65 | 930 | 525 | 1,400 | 450 | 2,645 | 1,040 |
| 5 | Private Forest Acquisition Act | 550 | 150 | 370 | 125 | 450 | 100 | 1,370 | 375 |
| 6 | Land partition / division | 3,500 | 750 | 3,400 | 700 | 3,200 | 650 | 10,100 | 2,100 |
| 7 | Registration of legal heirs | 4,100 | 1,500 | 3,500 | 1,200 | 3,100 | 1,100 | 10,700 | 3,800 |
| 8 | Displacement/ Other | 0 | 0 | 265 | 153 | 0 | 0 | 265 | 153 |
|  | Sub total Other Land Issues | 12,353 | 3,691 | 9,480 | 3,085 | 10,050 | 2,774 | 31,883 | 9,550 |
|  | Total | 15,668 | 5,153 | 12,967 | 4,530 | 13,112 | 4,024 | 41,747 | 13,707 |

ii.	Panchayati Raj

Eight meetings were organised in villages to discuss various aspects related to provisions of Panchayati Raj for village development. Importance was given to discussions on Ration Cards, BPL listing, Antyodaya Yojana, Housing Schemes, Drinking Water, Gaothan/ Gharthan and land issues for which it is important to pass resolutions in the Gram Sabha. Adivasi people were encouraged to attend Gram Sabha and to ask questions to elected representatives.

A training camp on Panchayati Raj was organised for elected representatives at Pathgaon in Murbad Taluka. Nine members were present. The Gram Sabha members were given inputs on issues like Gaothan, Gharthan, Encroachments, Unregistered tenants, 32 G, etc.

ADS then generated a list of all Adivasi elected representatives in Karjat and Khalalapur Talukas. The details are as given below:

Khalapur Taluka

| Sarpanch | Up Sarpanch (Deputy) | Members | Total Adivasi members |
| --- | --- | --- | --- |
| 4 Katkari men + 3 Katkari women + 1 Thakur man + 1 Thakur woman | 5 Katkari men | 23 Katkari men + 21 Katkari women + 12 Thakur men + 8 Thakur women | 78 Adivasi Gram Sabha members in Khalapur Taluka; 56 Katkari members |

Karjat Taluka

| Sarpanch | Up Sarpanch (Deputy) | Members | Total Adivasi members |
| --- | --- | --- | --- |
| 3 Katkari men + 4 Katkari women + 2 Thakur man + 1 Thakur woman | --- | 26 Katkari men + 18 Katkari women + 37 Thakur men + 18 Thakur women | 109 Gram Sabha members in Karjat Taluka |

Meetings and training sessions will be organised for elected representatives on Panchayati Raj issues in days to come. The objective is to motivate and orient elected representatives to play an effective role in the development process, with emphasis on addressing problems of the Katkari community. A similar approach is being followed by NGO partners in other Talukas.

iii.	Promoting bio-diverse agriculture in Katkari villages

Agriculture is perhaps the only source of livelihood that can enable Katkari people to live with dignity and self-esteem. ADS and partner NGOs are creating awareness about agriculture-based livelihoods in Katkari villages. ADS is motivating Katkari families to cultivate Dalli and Eksali lands which have been lying fallow since a long time.

The diminished availability and consumption of diverse uncultivated and cultivated foods from forests and fields is leading to a decline in the dietary diversity and increasing malnutrition amongst Katkari people. Several research studies throughout the world have established linkages between plant biodiversity and malnutrition.

Realising the need to promote bio-diverse agriculture in Katkari villages, the ADS team organised a campaign in 15 villages and assisted over 80 Katkari families to grow a wide range of food crops on their land.

Plant Biodiversity and Malnutrition: Simple Solutions to Complex Problems

“Globally, simplification of the diets of a large number of people to a limited number of high-energy foods as a result of urbanisation and socioeconomic changes presents unprecedented obstacles to human health associated with emerging diseases such as diabetes, hypertension and cancer. Greater use of plant biodiversity based on scientific evaluation of plant properties, cultural support programs, dietary education, innovative processing and marketing provides a possible avenue for mediating the impacts of change. The diverse nutrition and health functions that plants serve in traditional culture, and indigenous knowledge of plant diversity, offer potential valuable solutions that enable biodiversity to address the problems facing contemporary society. This paper summarises empirical evidence supporting the hypothesis that dietary diversity is essential for health and that biodiversity can be equated with dietary diversity.”

For full paper, refer: Timothy Johns; African Journal of Food, Agriculture, Nutrition and Development. pp 45-52, Vol 3, No. 1, 2003.

The ADS team distributed seeds/ planting material of Turmeric, Elephant’s foot yam, Colocasia, Karande (Dioscorea tubers), Chai, (Dioscorea tubers), Okra, Cluster bean, Cow pea, Tondli (Coccinea spp), Hadga  (Sesbania spp), Til (Sesame), Hulga (Horse gram), Udid (Black gram), Pumpkin, Bitter gourd, Sweet Potato, Ground nut, Cucumbers, Guava and Chilly.

Seeds/ planting material of these crops was collected from farmers in other regions. A campaign was then organised to create awareness about the importance of growing and consuming diverse foods.  Cultivation and consumption of diverse foods will hopefully bring about improvements in the nutritional status, apart from enabling Katkari families to earn additional income through sale of surplus tubers.

iv.	Collective farming by landless Katkari people

Landless people cannot grow food for their families and have to depend on manual labour for their livelihood. However, some landless Katkari families have been taking land on lease from other farmers who have surplus land. The terms of lease, though are generally unfavourable and the Katkari family ends up doing a lot of work for nothing. As an alternative, ADS decided to assist groups of landless Katkari families to come together and bargain a favourable lease agreement. Members of the group have collective strength and can contribute their own labour in the field.

ADS assisted 4 groups of 32 landless families to take up collective farming on 16 acres of land. Each family will be able to get 200-250 Kg of food grains after paying lease to the land owner.

ADS formed the groups and assisted them in negotiating the lease agreements; procuring seeds/ manures and in organising ploughs/ bullocks, etc.

Collective farming is helping landless Katkari families grow food grains for home consumption.

v.	Government food security programme

ADS has been attempting to improve functioning of Government food security programmes, particularly for Katkari families. The consistent work on land issues and lobbying with the Tribal Affairs Ministry at the state as well as central level on the issue of food security began yielding results. Things also started moving as a result of media reports in mid-2004 about malnutrition related deaths of Adivasi children in Maharashtra.

The District and Taluka administration invited ADS for a meeting to gain a better understanding of the prevailing situation and to evolve an action programme. It was decided that the Collector and Tehsildar will organise a meeting to improve functioning of the government food security programmes. ADS campus was chosen as a venue for the meeting since ADS was engaged in mobilising Adivasi people to attend the meeting. The meeting took place on 20th July 2004. Over 400 Adivasi people came for the meeting despite heavy rains and the transplanting season for rice and finger millet.

The Government had coined a catchy slogan for the meeting, “The Adivasi in Maharashtra will no longer remain hungry”, admitting in a way that they have been hungry all along. Government officials provided detailed information about the existing government food security programmes, particularly the targeted PDS System. ADS staff made presentations on how Katkari families were sidelined, pointing out loopholes in government programmes. Presentations were also made on the Grain Bank and the alternative PDS programmes implemented by ADS.

The meeting was then thrown open for Adivasi people to voice their grievances and to register their demands. A large number of Katkari families were facing difficulties in obtaining ration cards, BPL cards, caste certificates or in enrolling for the Antyodaya Anna Yojana and so on and so forth. People also complained that the Fair Price Shops did not function properly. Government officials gave an assurance that they would look into these complaints. Rationing Department officials were asked to take note of the complaints and to act on them. It was also decided that the Tehsildar himself should hold 3-4 camps in different regions with the ADS team to sort out matters related to legal documents for Katkari families on a priority basis.

Accordingly, three camps were held at Kalamb, Kadav and Neral between 20-28 August, 2004. More than 1,500 Adivasi families attended the camps. Government officials and ADS staff assisted the people to submit applications and to obtain required documents. 810 applications regarding Ration Cards (50 for new ration cards and 760 for removing/adding names to existing ration cards), 325 applications for Antyodaya Yojana and 120 applications for BPL listing were processed during the meetings. Out of these, Government has already issued 50 new ration cards while the applications for changes in names will take upto three months. Similarly, 325 applicants were issued Antyodaya Yojana cards. ADS is regularly following up with Government officials on these matters.

ADS staff invested a lot of efforts in visiting a number of villages, organising meetings to explain the purpose of the government initiative and helping people to do the home work before coming for the meeting with government officials. Despite the heavy rains and the difficulties in travelling to remote villages, it was a worthwhile experience since a large number of poor Adivasi families were able to benefit. More importantly, the process is helping bridge the gap between Government and people.

Government food security programmes/ schemes

- Targeted Public Distribution System (T-PDS): All Below Poverty Line (BPL) card holders must get 35 kg of grain per month at no higher than a subsidised price fixed by the state government. Rice – 18 Kg @ Rs. 6 per Kg; Wheat – 17 Kg @ Rs. 5 per Kg.

- Antyodaya Va Vistarit Antyodaya Yojana: All Antyodaya Yojana card holders must get 35 Kg of grain each month. Rice – 20 Kg @ Rs. 3 per Kg; Wheat – 15 Kg @ Rs. 2 per kg. The scheme is meant only for the poorest of the poor.

- Food for Work (FFW): Every person needing work in famine/ drought/ scarcity affected area must be given work in accordance with the terms of the state's famine/ relief/ scarcity code.

- Employment Assurance Scheme (EAS): at least two able bodied adults per family regardless of APL / BPL status who need work must be given at least 100 days of employment each, per year during the lean agricultural season. This scheme has now been merged under the Sampoorna Grameen Rojgar Yojana.

- Mid Day Meal Scheme: All children regularly attending government and government-assisted primary schools must be provided hot, cooked, midday meals for at least 200 days in a year.

- National Maternity Benefit Scheme (NMBS): Every pregnant BPL woman must be given Rs. 500 for the first two births, 8 to 10 weeks prior to delivery.

- National Old Age Pension (NOAP): All destitute persons 65 years and over, must receive Rs. 75 per month in addition to entitlements under the state pension scheme.

- Annapurna Scheme: All destitute persons 65 years and over eligible for central pensions (NOAP) but not receiving it must be given 10 Kg of free food grain (either wheat or rice or both) per month.

- National Family Benefit Scheme (NFBS): Every BPL family must get Rs. 10,000 cash on the death of the primary breadwinner.

- Integrated Child Development Scheme (ICDS): Supplementary nutrition, immunisation, health check ups, referral services, nutrient and health education must be given to all children upto 6 years of age, pregnant women and nursing mothers, adolescent girls, and malnourished children.

As per ICDS, it is the right of every:

- Child up to 6 years of age to get 300 calories and 8-10 grams of protein per day;

- Adolescent girl to get 500 calories and 20-25 grams of protein per day;

- Pregnant women and each nursing mother to get 500 calories and 20-25 grams of protein per day;

- Malnourished child to get 600 calories and 16-20 grams of protein per day.

vi.	Antyodaya Yojana

Bhima Malhar Waghmare is a poor Katkari from Vaijnath Katkarwadi. His family of 5 members lives in abject poverty, being landless and assetless. Bhima’s family works on a brick unit and also as agricultural labour to eke out a living. Each month Bhima was buying food grains worth Rs.500 from the market and the PDS by borrowing money from the contractor. He was sad to see well-to-do non-tribal persons in the next village availing benefits of the Antyodaya Yojana and getting 35 Kg of food grains each month at very low rates when his family starved at times.

ADS assisted Bhima to enrol for the Antyodaya Yojana by submitting his application to the Tehsildar. Bhima started getting 35 Kg of food grains each month for as low as Rs.90. Now he does not have to borrow money from the contractor.

Antyodaya Yojana card holders get 35 Kg of grain each month at a very low price of Rs. 3 per Kg for rice and Rs. 2 per Kg for Wheat. The scheme is meant only for the poorest of the poor. However, as with other schemes, Government has once again shown utter disregard in selecting ‘beneficiaries’. As a result, many well-to-do non-tribal persons were selected for the scheme while poor and starving Katkari families were left out. ADS did a case study of the scheme in 10 villages to point out weaknesses in implementation and presented it to the Tehsildar. It was vividly brought out that most needy Katkari families were left out of the scheme while a large number of non-tribal families had managed to get membership, thanks to the negligence by the Government. This coincided with adverse media publicity about starvation deaths and the Government was forced to extend the scheme to Katkari families. The Tehsildar requested ADS to enrol Katkari families for the Antyodaya Yojana. The ADS team spread out to a number of Katkari hamlets and managed to enrol over 900 poor Katkari families for the Antyodaya Yojana. These families are now able to buy 35 Kg of food grains per month at extremely low rates. The scheme is of particular importance to the Katkari community since most of them do not have adequate food grains in the house and generally buy food grains from the market as and when they have money.

vii.	Caste Certificate

Caste certificates entitle Adivasi people to access various Government programmes and schemes. They also enable Adivasi people to benefit from the reservations in the educational field and in Government jobs. However, obtaining a Caste Certificate can be a nightmare for an Adivasi person since it entails producing 22 different documents along with the application. Getting these 22 different documents from the bureaucratic Government officials at the Taluka level could take several months and a lot of money. Consequently, a large majority of Katkari families do not have Caste Certificates and are deprived of benefits offered by Government.

With several protests from civil society groups, the Government passed a Circular on 23 March 1999 (Circular No: STC-1098/C.N.92/Off 10) directing the Project Officers of the Integrated Tribal Development Project (ITDP) to issue Caste Certificates to Katkari people with minimum documents after verifying their claims through proper means.

ADS prepared a detailed note in Marathi explaining the process of obtaining Caste Certificates and organised awareness programmes in Katkari villages to utilise the provisions listed in the Government Circular of 23 March 1999.

The ADS team prepared applications for Caste Certificates on behalf of 88 Katkari persons from Male, Pashane, Jambhulwadi and Mohachiwadi. ADS requested the Tehsildar and Deputy Collector to organise special camps for Katkari people. The request was accepted and the first camp for Caste Certificates was organised at Neral on 29 July 2004. Sarpanch, Gram Sevak, Police Patil, Talathi, Tehsildar and ADS representatives were present for the camp. Applications were submitted on behalf of the 88 Katkari persons. These were processed, verified and submitted to the Project Officer, ITDP for approval. Caste Certificates were subsequently issued to 88 Katkari persons. Buoyed with the success, applications for Caste Certificates are now being prepared for 300 Katkari families from Nandgaon, Jamrukh and Rajpe.

viii.	Legal Documents and the Katkari community

The Katkari community is prone to exploitation by outsiders. An important instrument of exploiting Katkari families is the control of all their legal documents (land deeds, ration cards, caste certificate, etc). The contractors take away the legal documents from Katkari families who are bonded to them and then they are free to do whatever they want to do with the Katkari. This could even mean beating up and killing Katkari people or sexually exploiting the women.

The ration card of many Katkari families is always with the shop owner who misuses the card to swindle food grains entitled to Katkari people. Katkari people do not dare to ask for their documents or to protest. They suffer in silence.

Sakharam Mahadu Chavar is an old Katkari person in Male Katkarwadi, Karjat Taluka. He was working as a bonded labour on a brick unit for a contractor at Badlapur, about 30 Kms away from his village. One day, a friend of the contractor threw him off the road while recklessly driving a motrcycle. Sakharam was severely hurt and had complex fractures in his hip bone, thigh and leg. The contractor took away Sakharam’s documents and threatened him with dire consequences if he were to file a police case. Sakharam was sent back to his village since he was not in any position to work on the brick unit. The villagers took him to a government hospital near Mumbai where he was given some treatment. However, Sakharam’s fractures were not treated since he did not have the money the doctors were demanding for an operation. Moreover, he did not have any means to seek medical help since his legal documents were with the contractor.

Sakharam went back to his village once the superficial wounds had healed. From then onwards Sakharam has lived in a small hut with his wife. They do not have any source of income and their condition can only be described as desolate. Sakharam’s legs are bent and he is unable to walk or even get up without the support of two sticks. Sometimes, he stands outside his hut holding a horizontal wooden beam someone has put in place.

Sakharam’s legal documents are still with the contractor who does not want to return the documents to prevent possibilities of a police case. However, the loss of documents deprives Sakharam of all government schemes (including subsidised food grains) and concessions that he could have availed.

There are many Sakharam’s amongst Katkari people. And they have a similar story to narrate.

Another important aspect in this whole affair is the difficulty which Katkari people face to obtain the legal documents from Government officials in the first place. It takes them many trips to the Taluka Head Quarter and a lot of money to collect basic documents. If any document is lost, misplaced or stolen, the Katkari person has to once again spend a lot of time, effort and money to get back the documents from Government officials.

ADS is considering setting up a “Document Bank” for Katkari people in the region given the importance of legal documents to poor Katkari families and their use as means of exploitation. The bank will hold the originals of all legal documents; issuing xerox copies on request. The Document Bank will also scan important legal documents and store them electronically. A beginning has already been made by collecting land deeds of 175 Katkari families. ADS will give a proper shape to the Document Bank over the next 2-3 years.

ix.	Legal advice and assistance

A major reason for the continuing exploitation and persecution of Katkari people is perhaps their ignorance and fear of government rules, regulation and legalities. Atrocities against Katkari people often go unnoticed and/or unpunished. With this in mind, ADS began organising fortnightly “Legal Aid Camps” for Katkari people. ADS offered legal advice on issues like land matters, criminal cases, internal disputes, inter-village disputes, atrocities by outsiders, civic amenities, etc.

For the Katkari, the law enforcing agencies themselves are a source of persecution since the community is treated as a “Criminal Tribe” even today. Katkari people are often arrested and put into prison for no rhyme or reason. In the process they may get beaten up by the police and forced to admit crimes which they have not committed.

Katkari youth from Khalapur Taluka narrate incidences of how the police arrest them even if they are seen in Chowk town in small groups of 4-5 persons. There are restrictions which force them not to go out in groups!

Katkari people do not have recourse to legal norms which apply to other Indian citizens. This is hence a fundamental human rights violation against the Katkari community!

ADS organised fortnightly legal aid camps. ADS inputs consisted of:

- Explaining legal aspects in a simple language,

- Assisting Adivasi people to submit applications for land issues,

- Discouraging criminal and anti people activities,

- Facilitating village-level meetings to resolve disputes,

- Filing police cases for atrocities against the Katkari,

- Writing and submitting applications on behalf of Adivasi people,

- Following up with Government.

Details of the legal aid offered by ADS during the reporting period are as follows:

| No. | Issue/ Matter | Number of cases | Action |
| --- | --- | --- | --- |
| 1. | Land matters | 265 | Provide legal information; assist in obtaining basic documents and in preparing application for submission to Government; submit collective applications; follow up with Government offices; etc. |
| 2 | Police Cases | 30 | Legal guidance; assist in submitting applications; etc. |
| 3 | Internal disputes | 58 | Persuade the parties concerned to resolve disputes through dialogue instead of going to the Police, organise village-level meetings to resolve the disputes within the village; try and strengthen the traditional dispute redressal forums. |
| 4 | Inter village disputes | 6 | Organise meetings in both villages to diffuse the crisis and persuade people to resolve the conflict through peaceful means; organise joint meetings; offer legal guidance; etc. |
| 4 | Atrocities by non-tribals | 8 | Provide legal guidance; organise villagers; file police cases; exert collective pressure; etc. |
| 5 | Civic amenities | 19 | Provide information about existing Government schemes; assist in preparing and submitting applications; encourage people to discuss the issue in the Gram Sabha; etc. |
| 6 | Forest plots | 14 | Provide legal information; assist in preparing and submitting applications; follow up with Government; etc. |

The legal aid camps are proving to be so effective and popular that the Government is keen to follow the example, perhaps in efforts to be seen as pro-Adivasi and pro-poor. The Tehsildar has announced a one-day legal aid camp for Adivasi people on ADS campus during October 2004. A retired High Court Judge will provide legal guidance and government officials will try and sort out pending issues.

A group of six Katkari families from Talavli village in Khalapur Taluka annually migrate to a brick unit in the distant Vavanje village in Panvel Taluka. One of the Katkari men from this group, Chandrika Pawar, requested a two day leave from the contractor to go home for meeting a sick relative. The contractor was so angry that he and his men rounded up all the six Katkari men on the brick unit and beat them up mercilessly.

The six Katkari men ran away in the night and contacted ADS. The ADS team immediately went to the brick unit with the six Katkari men and told the contractor that they were filing a police case against him for physically assaulting the Katkari people. He was explained the consequences. The contractor was frightened. He immediately agreed to provide compensation, medical care and to personally apologise to each Katkari person; assuring them that this kind of incidence will not take place in the future. He also agreed to pay them wages as per mutually agreed upon terms. The Katkari people then decided not to go to the Police since long-term employment with the contractor was more important for them.

x.	Education for Katkari children

Katkari children and schools have not been able to go together for one reason or another. A major cause is the annual migration of Katkari families to distant brick kilns. Extreme poverty and the lack of an enabling atmosphere create hurdles and mind blocks in the minds of Katkari people. The rigid and constricted atmosphere in schools does nothing to encourage Katkari children to attend schools. On the contrary, it goes against their attitude and culture. There is a need perhaps to set up alternative schools that can allow and encourage Katkari children to learn in an open and uninhibited atmosphere.  ADS will pursue the dream of separate schools for Katkari children in years to come. For the time being, ADS has started creating awareness about the importance of education in Katkari villages. Awareness meetings were organised in 50 villages and efforts were made to motivate parents to send their children to schools. 30 children have started attending school. However, the school dropout rate is extremely high and special efforts would be needed to sustain the interest of Katkari children. Much more will have to be done at the education front in years to come.

xi.	Media exposure

A number of articles and reports have been prepared and published in regional language publications (newspapers and magazines) on issues pertaining to the Katkari by the ADS team. The objective is to create awareness about the plight of the Katkari and to make public malfunctioning of government programmes.

xii. Conclusion

The progress during the first six months of a focussed initiative with the Katkari has already shown wonderful results. It is unfortunate that the government is spending much more money without really achieving anything.

ADS will attempt to monitor and influence government programmes in years to come. ADS and partner NGOs will themselves continue the efforts that they have initiated with support from the Onaway Trust, Rainforest Information Centre and Grassroots.

Annexure I

Dalli and Eksali lands: an unresolved dilemma

Dalli and “Eksali woodland plots” are plots of land legally given on lease to landless people (mainly tribals) for cultivation of crops by the forest department in Raigad and Thane Districts of Maharashtra. The practice of allotting Dalli and Eksali lease, which was said to be in vogue even during the rule of Peshwas, was given a formal and legal character somewhere around 1875 as an attempt by the British Government to prevent shifting cultivation by tribals in forest areas. Tribals were encouraged to practice settled agriculture on the leased plot and to pay a tax to the government. Ownership of Dalli and Eksali lands was retained by the Forest Department.

There is a distinction between Dalli and Eksali systems. Dalli lands are given on lease collectively to a group of farmers while Eksali plots are given to individual farmers. The Forest Department issues a proper “Pass Book” for each Dalli Plot in the name of the Dalli Naik, who is the leader of the group. The Pass Book gives details of the Dalli Plot in terms of the survey number, total area, name of the village, name of the Dalli Naik, names of other tenants, number of members in each tenant family, amount of tax payable, rules and regulations applicable to the Dalli Naik, etc. Dalli plots are much larger in size (at times above 100 acres) while Eksali plots are smaller in size. The Dalli system is found mainly in Raigad District and Eksali is common in Thane District. The system of Eksali is also prevalent in some other Districts. The area of Dalli land in Raigad District is about 33,000 acres while Thane has over 28,000 acres of Eksali woodland plots. More than 30,000 tribal families are cultivating the Dalli and Eksali lands. The State Government has issued GRs during 1969-1971 stating that the ownership of Eksali and Dalli plots should be legally handed over to tribal cultivators. However, tribals have not become owners of Eksali and Dalli plots due to the indifferent attitude of government agencies.

Another important aspect about Dalli and Eksali is the fact that a large number of plot holders are Katkaris, a marginalised and “Primitive Tribal Group”.

Fate of Eksali and Dalli plot holders seems elusive even 30 years after the government orders. Most tribal families who have been cultivating Dalli and Eksali plots for decades are still landless.

# Legal aspects

A decision to release Eksali Land permanently to the cultivators was taken by the Government of Maharashtra on March 22, 1969 whereas the decision with regard to Dalli Land was taken on 14 January, 1970 vide Government Resolution (GR No. FLD/4288/27023-W). However, it was stated in the resolution that only cultivable land should be given to tribal farmers. A modified resolution, setting aside the criteria of fitness or suitability of land, was issued on 26 July, 1971 (FLD 4268/ 27023- W). As part of this resolution, tribal farmers were to get ownership of Dalli lands.

The Government Resolution of 1971 states that “Government has decided that all the available Dalhi lands should be disforested and granted to these Dalhi plot holders. ….. all the 29,000 acres of Dalhi land should be distributed among the 6,500 plot holders. The Chief Conservator of Forest should now take further immediate steps regarding disforestation, removal of tree growth, survey and demarcation of these lands and grant of these lands on permanent basis”.

The forest department began work on disforestation sometime afterwards. Over 1,000 Ha of the ‘disforested’ Dalli land was handed over to the Revenue Department for further transfer to Dalli plot holders. However, the state government did not give ownership of the Dalli / Eksali land to cultivators. Activists, NGOs, CBOs and other civil society groups came together under the banner of Shoshit Jan Andolan to fight for the cause of Dalli and Eksali plot owners in Raigad and Thane District.

In the meanwhile, the Forest Conservation Act came into being in 1980 and subsequently the Maharashtra Government began citing the need for permission from the Ministry of Environment and Forests for transferring forest land to a non-forest purpose. The campaign by Shoshit Jan Andolan intensified during this period.

On 13 February, 1987 the Bombay High Court passed a judgment on a petition filed by Vishwanath Kisan Jadhav, a farmer from Solapur District, on ownership rights for Eksali plot. The division bench decided that the insertion of the subject of forest in the concurrent list and passing of the Forest Conservation Act (1980) will have no bearing on this case and the state government was directed to transfer the land on permanent tenure in favour of the petitioner.

NGOs/ CBOs exerted a lot of pressure at the state and central government levels. Subsequently the Ministry of Environment and Forests issued a circular on 18 September 1990 stating that the provisions of the Forest Conservation Act, 1980 would not be binding on the decision taken by the State Government before its enactment.

Shoshit Jan Andolan filed a writ petition in the Supreme Court of India in October 1995 to ensure implementation of recommendations contained in the circular of the Ministry of Environment and Forests of 18 September 1990. The court reprimanded the state government and asked it to form distinct committees to solve the matter immediately.

Subsequently, the forest department initiated surveys of Dalli lands but there was no move to hand over legal ownership. The state government kept pointing fingers at the central government (Ministry of Environment and Forests) while the centra1 government refused to entertain any requests for concrete action on the matter.

A writ petition was filed by the Shramik Mukti Sanghatna on 19 November 1998 (WP No. 4431 of 1995) for the implementation of the government resolution of 22 March 1969 on Eksali lands. The High Court directed the state government to give legal land deeds to all Eksali plot owners within a year.

Despite the government orders, struggles, campaigns and court judgments, the fate of Dalli/ Eksali plot owners is uncertain even 30 years after the government order to hand over legal ownership of land to tribal farmers. On the contrary, the state government has given an indication resisting moves for handing over ownership of land to Dalli and Eksali plot owners. Forest department officials have instead suggested using Dalli and Eksali lands for Joint Forest Management (JFM) programmes. Over 30,000 poor tribal families will be displaced from the lands that they have been cultivating for decades if the government succeeds in its plan to divert Dalli and Eksali lands to other uses.

There is a need to sort out the confusion between the state and central government and to get the state government to adhere to its orders of 1969 and 1971. A beginning can be made by getting MoEF to issue a categorical statement, stating that the Forest Conservation Act (1980) will not have any bearing on the Government Resolution of 1969 and 1971. The state government can then be forced to act.

Shoshit Jan Andolan constituents:

Shramik Kranti Sanghatna, Sarvahara Jan Andolan, Gram Swarajya Samiti, Shramik Adivasi Samajonnati Mandal, Jagrut Kashtakari Sanghatna, Kashtakari Sanghatna, Bhumi Sena, Shramjivi Sanghatna, Shramik Mukti Sanghatna, Samata Andolan

Note: Other campaigns and/ or activists may also have been associated with Shoshit Jan Andolan at various points in time.

What can be done?

Any development strategy in the Konkan region should accord top priority to sorting out the Dalli / Eksali issue. Over 30,000 tribal families (particularly Katkaris) would get legal ownership of more than 60,000 acres of land. However, the civil society organisations and campaigns involved in these issues need to do a lot of homework in order to present a foolproof case to the government.

A majority of the Dalli and Eksali plot holders are landless tribal families. There is lack of comprehensive data to establish a correlation between the lease and the socio-economic and other well-being indicators of the plot holders.

It is extremely important to collect/ generate the following information about Dalli/ Eksali lands:

- Total Dalli and Eksali land in Raigad and Thane District (Taluka-wise).

- Actual number of Dalli and Eksali plot holders (as of today).

- Social / ethnic profile of plot holders.

- Land holding pattern amongst the Dalli / Eksali plot holders. How many own land other than the Dalli / Eksali plot? What is the percentage of landless people?

- Land use pattern in Dalli / Eksali plots. Land under cultivation, paddy land, millet land (varkas), vegetable cultivation, fruit trees, other economic trees, forest, barren land, etc.

- Encroachment on the plots.

- Number of houses, villages on the leased land.

- Socio-economic profile of representative samples of Dalli / Eksali plot holders from each Taluka in Thane and Raigad Districts.

- Food security benefits for representative samples from Dalli/ Eksali land of each Taluka.

- NTFP benefits to tribal communities from Dalli/ Eksali land.

The biggest challenge in efforts to resolve the issue is to seek participation of all those who are trying to address the issue of Dalli / Eksali lands. The time has come to “get together” and to exert a collective push.

Work on assisting the Dalli / Eksali plot holders to earn their livelihoods from the land would have to be initiated once they have legal ownership of land. This in itself would be a gigantic task. There is a need to engage each other further on this issue on a priority basis.

Note prepared by:

Rajeev Khedkar / Bansi Ghevde

Academy of Development Science

Kashele Post, Karjat Taluka, Raigad District

Maharashtra 410 201

Date: May 2004

References/ Sources of information:

- Article on Dalli lands by Surekha Dalvi and Milind Bokil in EPW.

- Discussion with Bansi Ghevde, Dnyaneshwar Patil and Vijay Sathe.

- Visits to Katkari villages and discussion with Katkari people.